## GMPP
Project Name | IT Transformation Programme | NCA Transformation Programme
Department | NCA | NCA
IPA Delivery Confidence Assessment (A Delivery Confidence Assessment of the project at a fixed point in time, using a five-point scale, Red – Amber/Red – Amber – Amber/Green – Green; definitions in the MPA Annual Report) | Amber | Amber
Description / Aims | IT Transformation is one of three programmes that together comprise NCA Transformation, which seeks to move the Agency from a legacy IT estate to a modern environment that will support the NCA's technology and information needs, realising the vision of the programme - “Create a cutting edge technology and information environment that connects, empowers and enhances our officers’ crime fighting capabilities”. | The NCA’s Transformation Programme which will enable the NCA to become an intelligence-led and digitally- driven organisation. Our current capabilities and operating model limit our ability to relentlessly disrupt the changing threats – especially internet - and digitally related threats.The NCA's Transformation Programme will deliver the culture, capability and capacity to enable the NCA to be a world-class law enforcement agency, leading the work to cut serious and organise crime.
Departmental commentary on actions planned or taken on the IPA RAG rating. | The IPA Review Team made 7 recommendations when the Amber rating was awarded in September '16. Six of these recommendations have now been acted upon and closed. One recommendation is ongoing. The next Gateway Review (Gate 1) takes place w/c 3 April | The current status of the NCA Transformation Programme is Amber reflecting the on-going development of the Programme. The recently completed Integrated Programme Plan will ensure that the scope, dependencies and risks are understood across the whole Programme and will aloow informed decsions to be made around priorities and sequencing.
Project - Start Date (Latest approved start date) | 2016-04-01 | 2014-04-01
Project - End Date (Latest approved end date) | 2022-07-31 | 2019-03-31
Departmental narrative on schedule, including any deviation from planned schedule (if necessary) | Schedule on track | Schedule on track
2016/17 TOTAL Baseline £m (including Non-Government costs) | 14 | 25.5
2016/17 TOTAL Forecast £m (including Non-Government costs) | 14 | 25.5
2016/2017 Variance %age | 0% | 0%
Whole Life Cost TOTAL Baseline £m (including Non-Government costs) | 168.6844 | 306.8
Departmental narrative on budget/forecast variance for 2016/17 (if variance is more than 5%) | Variance less than 5% | Variance less than 5%
Departmental Narrative on Budgeted Whole Life Costs | Whole life costs continue to be on target | Whole life costs continue to be on target.
ID Numbers | NCA_0002_1617-Q2 | NCA_0001_1415-Q2
Annual Report Category | ICT | Government Transformation and Service Delivery