## Sheet1
GMPP ID Number | Project Name | Department | Annual Report Category | Description / Aims | IPA Delivery Confidence Assessment (A Delivery Confidence Assessment of the project at a fixed point in time, using a three-point scale, Red – Amber – Green; definitions in the IPA Annual Report on Major Projects) | SRO Delivery Confidence Assessment (A Delivery Confidence Assessment of the project at a fixed point in time, using a three-point scale, Red – Amber – Green; definitions in the IPA Annual Report on Major Projects) | Departmental commentary on actions planned or taken on the IPA RAG rating. | Project - Start Date (Latest Approved Start Date) | Project - End Date (Latest Approved End Date) | Departmental narrative on schedule, including any deviation from planned schedule (if necessary) | Financial Year Baseline (£m) (including Non-Government Costs) | Financial Year Forecast (£m) (including Non-Government Costs) | Financial Year Variance (%) | Departmental narrative on budget/forecast variance for 2021/22 (if variance is more than 5%) | TOTAL Baseline Whole Life Costs (£m) (including Non-Government Costs) | Departmental Narrative on Budgeted Whole Life Costs | TOTAL Baseline Benefits (£m) | Departmental Narrative on Budgeted Benefits
NCA_0001_1415-Q2 | NCA Transformation Portfolio | NCA | Government Transformation and Service Delivery | The NCA's Transformation Portfolio will enable the NCA to become an intelligence led and digitally driven organisation. Our current capabilities and operating model limit our ability to relentlessly disrupt the changing threats, especially internet and digitally related threats. The NCA's Transformation Portfolio will deliver the culture, capability and capacity to enable the NCA to be a world-class law enforcement agency, leading the work to cut serious and organised crime. | Amber |  | The Infrastructure Project Authority's Delivery Confidence Assessment rating at 22/23-Q4 is Amber. This is primarily due to the following factors. Programme leadership, governance and assurance has been a key focus for the Agency following the 2022 IPA Gate 0 Review. A governance review included launching an Executive Committee which meets fortnightly, bringing the governance of Finance, Investment and Change closer together, appointing a new Transformation Director and strengthening our 2nd line assurance. In addition, there is a greater understanding of the workforce requirements and the skills required to deliver the agency ambition by reviewing our attraction strategies to encourage people to work for the agency and considering how we use our commercial contracts to ensure the best value for money. This year embedding benefit realisation into our performance framework is critical so that our governing boards focus on delivery that impacts on operational performance, and we will continue to develop our capability model to move away from a Command approach to define our future requirements. | 2014-04-01 | 2030-03-31 | Compared to financial year 21/22-Q4, the project's end-date at 22/23-Q4 remained schedule to finish on 2030-03-31. This is primarily due to the following factors. There has been no deviation from schedule as the NCAs Transformation Programme remains aligned to the Agencys Strategy 23 28. The Transformation Programme (the portfolio) has been delivering since 2014, and continues to build capability and set the basis for transformation of our digital, data and technology and future estates. These activities builds on and provide firm direction for the Spending Review (SR) period and sets the foundations for future investments in subsequent SR rounds. The forward plan is divided into three tranches Tranche 1 (SR period 22-24), Tranche 2 (SR period 25-27) and Tranche 3 (SR Period 28-30). | 320.62 | 320.62 | 0% | The budget variance is inferior or equal to 5%. None | 2184 | Compared to financial year 21/22-Q4, the project's departmental-agree Whole Life Cost at 22/23-Q4 decreased from 2189m. to 2184m. This is primarily due to the following factors. The decrease in whole life cost is as a result of aligning the WLC to the approved FY 22/23 Portfolio Business Case. There has been no change in forecast in future years at this stage. | 3086 | The project's departmental-agree monetised benefits at 22/23-Q4 is 3086m. The benefits figure is driven by the NCA Portfolio Business Case v1.2 and the contributing Programme level benefits. Benefit actuals are currently in the process of validation by the programme and the end of year benefit position will be available for reporting in Q1 of FY 23/24.